## Risk Register
Risk ID | Risk Category | Risk Description | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Risk Owner | Current Controls | Treatment Action | Status
R001 | Cybersecurity | Unauthorised access to customer payment data by external hacker | 4 | 5 |  | Critical | IT Security Manager | Firewall, SSL encryption | Implement MFA and conduct penetration testing | Open
R002 | Cybersecurity | Employee clicks phishing email and exposes login credentials | 5 | 4 |  | Critical | IT Security Manager | Spam filters, email security | Conduct phishing simulation training quarterly | Open
R003 | Operational | Payment system crashes causing service unavailability | 3 | 5 |  | High | Head of Operations | Basic server monitoring | Implement redundant systems and disaster recovery plan | Open
R004 | Operational | Employee deliberately leaks or steals customer financial data | 2 | 5 |  | Medium | Chief Information Security Officer | Basic access controls in place | Implement role based access control and staff background checks | Open
R005 | Third Party | Cloud infrastructure provider experiences outage affecting Zenith payments | 3 | 5 |  | High | Vendor Risk Manager | Basic SLA agreement with vendor | Implement vendor risk assessments and backup cloud provider | Open
R006 | Compliance | Zenith fails to comply with Australian Privacy Act 1988 when handling customer data | 3 | 5 |  | High | Chief Compliance Officer | Basic privacy policy in place | Conduct privacy impact assessment and staff privacy training | Open
R007 | Cybersecurity | Ransomware encrypts Zenith systems and demands payment for restoration | 3 | 5 |  | High | IT Security Manager | Antivirus software installed | Implement regular data backups and incident response plan | Open
R008 | Financial | Fraudulent transactions processed through Zenith payment platform | 4 | 4 |  | Critical | Chief Financial Officer | Basic fraud detection rules in place | Implement AI fraud detection system and transaction monitoring | Open
R009 | Compliance | Zenith fails PCI-DSS audit resulting in fines and loss of payment processing licence | 2 | 5 |  | High | Chief Compliance Officer | Annual PCI-DSS review conducted | Engage external auditor and remediate all gaps before next audit | Open
R010 | Operational | Staff member accidentally sends customer data to wrong recipient | 4 | 3 |  | High | Head of Operations | Basic email policy in place | Implement data loss prevention tools and mandatory staff training | Open
R011 | Cybersecurity | Staff using weak passwords leading to unauthorised system access | 4 | 4 |  | Critical | IT Security Manager | Basic password policy exists | Enforce strong password policy and implement MFA across all systems | Open
R012 | Compliance | New Australian cybersecurity regulations introduced requiring immediate compliance | 3 | 4 |  | High | Chief Compliance Officer | Monitoring regulatory updates | Engage legal counsel and establish regulatory change management process | Open

## Risk Summary
Zenith Payments — Risk Register Summary
Company: | Zenith Payments Pty Ltd
Document: | GRC Risk Register
Prepared by: | Sandra Uneze
Date: | March 2026
Framework: | ISO 31000 Risk Management
Risk Level | Count
Critical | 4
High | 6
Medium | 2
Low | 0